APPN HiRes Protocol

Season Summary & Working Plan

Status: Active for current season

# 1. Purpose & Scope

This protocol consolidates the agreed pathway for HiRes drone-based plant imaging across APPN nodes for the current season. It covers (a) the field capture protocol, (b) the photogrammetry processing pipeline under development, (c) the parallel non-photogrammetry workflow, and (d) the team responsibilities required to deliver both pipelines. It applies to all upcoming flights this season, including plant emergence flights.

# 2. HiRes Field Protocol

## 2.1 Source & Status

- Field-tested on Tuesday; this now becomes the protocol for the season.

- Applies to all upcoming flights, including plant-emergence flights.

## 2.2 Node Pre-Flight Requirements

- Inspect and maintain the gimbal; perform a balance check (refer to video links in the Gitbook protocol).

- Record and confirm location (LOC) settings if not already done.

- Why: this becomes important for non-photogrammetry methods and for any future boresight calibration and is good practice regardless.

## 2.3 Flight & Capture Settings

| Setting | Requirement |
| --- | --- |
| Overlap | Maintain 80 / 80 overlap for photogrammetry. |
| Preferred processing | Photogrammetry is the preferred processing method for all work. |
| Exception | Mature crop “green deserts” that will not process in photogrammetry — use non-photogrammetry workflow. |
| Shutter speed | Fixed. |
| Aperture | Fixed. |
| ISO | Variable — use ISO to balance the histogram. |

# 3. Photogrammetry Processing Pipeline

Photogrammetry is the preferred processing route. A working team needs to be formed to build the pipeline; UQ has invested time and expertise to date and is expected to lead. The pipeline should be reproducible and minimise user discretion.

## 3.1 Pipeline Basics

- Leverage work already completed by UQ; use their methods as the starting point.

- Build on a photogrammetry solution using Agisoft Metashape.

- Convert raw IIQ files to lower-resolution JPEGs to drive efficient photogrammetry (initially).

- Automate processing in Python, driving Metashape and using GDAL tools.

- Remove any need for user input / discretion in the pipeline wherever possible.

## Plot Extraction & Labelling

- Pipeline must accept plot extraction inputs or shapefile / geographic locations of plots, plus plot labels.

- APPN plot-extraction method is required and must interface cleanly with these workflows.

- Once the photogrammetry solution is computed, clip images to plot boundaries and label each clipped image with its plot ID.

- Clipping should be lossless at native / maximum resolution.

- Resampled / lower-resolution outputs may be generated afterwards where downstream traits benefit.

- Clipped, labelled imagery feeds the downstream trait work.

# 4. Non-Photogrammetry Solution

A non-photogrammetry workflow remains necessary, particularly for mature “green desert” crops that fail in photogrammetry. Warin and Bipul are leading this work and will expand the team as required.

- PhaseOne Image SDK appears to offer much of the required functionality, including image conversion tooling (also relevant to the photogrammetry route).

- A reasonable working knowledge of the PhaseOne Image SDK GUI and code is required.

- Investigate whether boresight calibrations could improve image geo-location.

# 5. Team Responsibilities

Human resources from across nodes are required to deliver these pipelines. Indicative assignments below are proposals to be confirmed by each node.

| Person / Team | Proposed Contribution |
| --- | --- |
| UQ | Lead the photogrammetry pipeline build; contribute time and expertise. |
| Author (technical) | Contribute to the technical side of photogrammetry processing and Metashape settings. |
| James | Support pipeline development. |
| Dillon | Technical review (proposed). |
| Richard / Arden (USyd) | Support and advise (proposed). |
| CSU team | Provide technical input (proposed). |
| Bipul | Integration of tooling for image conversions, etc. (proposed). |
| Warin & Bipul | Lead non-photogrammetry pipeline; expand team as needed. |

# 6. Critical Outstanding Items

- APPN plot-extraction method: an agreed approach must be finalised; it is the interface between field outputs and both processing pipelines.

- Working team confirmation: node leads to confirm named contributors for the photogrammetry pipeline.

- PhaseOne SDK capability: confirm scope of Image SDK functionality and resourcing for GUI/code expertise.

- Boresight calibration: decide whether to pursue as a means of improving image geo-location.

# 7. Pre-Flight Quick Checklist

- Confirm you are working from current Gitbook protocol.

- Gimbal inspected, balanced; videos consulted as needed.

- Record / LOC settings captured.

- Flight plan configured for 80 / 80 overlap.

- Shutter speed fixed.

- Aperture fixed.

- ISO set to balance histogram on test frames.

- Crop assessed: if “green desert”, flag for non-photogrammetry workflow.